## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 101 | 8 |  |  |  | 21 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0
| 2016-10-03 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Mon | Mon | Mon | Mon | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-09-12 | 2016-09-14 | 2016-09-16 | 2016-09-19 | 2016-09-21 | 2016-09-23 | 2016-09-26 | 2016-09-28 | 2016-09-30 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 |  | ——Preparation—— | [23 empty] | Assigned
6 | 1 | Play / study original zelda game | ALL |  | 2 | 0 |  |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Google search "zelda nes online" and you should figure out how to easily play the game. Otherwise, visit the videogame archive in the basement of the Duderstadt. | Active
7 | 1 | Watch zelda tutorial (canvas) | ALL |  | 2 | 0 |  |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | There are two Zelda tutorials available for viewing. Read how they're different in the Piazza template repo. | Verify?
8 | 2 | Mess With 494 Quest (Piazza Bonus Template) | ALL |  | 2 | 0 |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 494 Quest was built for you to examine, pilfer, and learn from. | Fixed
9 | [25 empty] | Deferred
10 | [25 empty] | Fact of Life
11 | [25 empty] | Can't Repro
12
13
14
15 |  | ——Player Character——
16 | 1 | Grid-based movement | ME | EA | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1 | Health and damage cooldown (damage-invincibility) | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A nasty side-effect of not implementing a damage cooldown or "vulnerability-period" is that players die exceedingly quickly.
18 | 1 | HUD and Item Selection Capability (item menu). | EA | ME | 10 | 0 |  | This should be wayyyy longer | 10 | 10 | 10 | 10 | 6 | 6 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Building menus and simple inventory management systems is necessary in many games, and good experience to get. Be thankful you're not making Pokemon, like the F15 class did.
19 | 1 | Collectable Pickup Capability (Hearts, rupees, items) | ME |  | 1 | 0 |  |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1 | Bow Weapon Functionality | EA |  | 3 | 0 |  | still buggy fix me. weird thing with collisions | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | Boomerang Weapon Functionality | EA |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | The boomerang has many functionalities-- be sure to implement them all!
22 | 2 | Shield - Reflect projectiles. | EA |  | 2 | 0 |  | HAVE NOT TESTED TODO | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Haven't actually tested yet so we'll see if it actually works
23 | 1 | Bomb Weapon Functionality | EA |  | 2 | 0 |  | Make Bomb animation!! Ask Morgan about what he did for stunned state | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 3 | Basic Movement (Link) | ALL |  | 0 | 0 |  | THIS IS TAKING TOO LONG!! 11 hours, time for office hours... o.0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 |  | Fix link moving in attacking state then not animating
26 |  | FIX WEAPONS triggers not colliders adn stuff with walls
27 |  | LINK DEATH?? I just have it load the scene again if he dies
28 |  | Get boomerang sequence and boomerang object catch
29
30
31
32
33
34
35 |  | ——Enemies——
36 | 1 | Stalfos - Skeleton Enemies | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 1 | Keese - Bat Enemies | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 1 | Goriya - Boomerang Enemies | ME |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 2 | Bladetrap - Spike Obstacle Enemies | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 1 | Gel - Slow Enemies | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 2 | Wallmaster - Creepy Hand Enemies | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The wallmaster reset's Link's position in the dungeon, but not the dungeon itself! Don't be lazy and just call Application.LoadLevel()!
42 | 1 | Aquamentus - Dragon Boss | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
43 | 1 | Enemy generation in Game | EA |  | 3 | 0 |  | Not merged in master. Still in testing but is finished | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 1 | Enemy --> Item Drop (and drop-rates) | EA |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
44 | 1 | Link/ weapon and Enemy interaction | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46
42 | 1 | Aspect Ratio | EA |  | 1 | 0 |  | DONE! | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48
49
50 |  | ——Environment——
51 | 1 | Room Transitions | ME |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 1 | Locked Doors | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 1 | Pushable Blocks | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 2 | Old-Man Room (Simple Speech Engine) | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Speech and dialogue engines appear in many games, often as the primary driver of plot and character development. Zelda's dialogue system is simple, and provides an opportunity for experience.
55 | 2 | 2D Room (Bow Room) | ME |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
56 | 1 | Water tiles (allow projectiles but not physical entities) | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 1 | Room events | ME |  | 2 | 0 |  | Make a restart | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Like doors unlocking when all enemies are distroyed and keys being dropped
58 | 2 | Invincibility Clock | ME |  | 2 | 1 |  | This is the cheat code does not stop enemies | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
53 | 1 | Cheat Codes for submission | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 1 | Triforce and Heart Collection | EA |  | 1 | 0 |  | Triforce gets released when aquamentus dies | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
53 | 1 | Place enemies in room and handle their deletion | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 1 | Sound effects | ME |  | 1 | 0 |  | Triforce gets released when aquamentus dies | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
61 |  | --------Custom Level -----------------
53 | 1 | Make Map for rooms (and lay them out) | ME |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0
53 | 1 | Design the two blade trap puzzle rooms | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
53 | 2 | Make 2 blade trap puzzle rooms | ME |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
65 | 2 | Layout Enemies In custom level | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
65 | 2 | Locked doors and key locations for custom level | ME |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
67 | 1 | Design boss for custom level | EA |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
53 | 2 | Implement "Phantom bow" enemy | ALL |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | 2 | Gel only moves one block at a time | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
108 | 1 | East locked doors not opening right | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
109 | 1 | Locked doors close again when tiles reloaded | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
110 | 2 | Link not linearly interpolating through doorways | ME |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
111 | 3 | Fix Stutter at the end of link iterpolating through doorways | ME |  | 1 | 1 |  |  | 1 | [16 empty] | Reported | bar: 2016-09-12 to 2016-10-03
112 | 3 | Fix Keese getting stuck in walls ocassionaly | ME |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 21 | 21 | 19 | 17 | 14 | 12 | 10 | 7 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 101 | 101 | 91.381 | 81.7619 | 67.3333 | 57.7143 | 48.0952 | 33.6667 | 24.0476 | 14.4286 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 73 | 73 | 68 | 68 | 60 | 51 | 36 | 33 | 28 | 16 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 26 | 26 | 26 | 24 | 24 | 24 | 20 | 18 | 16 | 12 | 7 | 7 | 7 | 7 | 7 | 7
217 |  |  | 3 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Morgan Erlich | ME |  |  |  |  | ME | 61 | 61 | 60 | 60 | 56 | 48 | 35 | 31 | 28 | 16 | 6 | 6 | 6 | 6 | 6 | 6
223 |  | Eliana Abraham | EA |  |  |  |  | EA | 29 | 29 | 29 | 29 | 25 | 24 | 18 | 17 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0
224 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 |  | All | ALL |  |  |  |  | ALL | 11 | 11 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2
226 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101 | 101
236

## Daily Scrum
Producer | 2016-10-03 |  | Team Members
Approved | Dates |  | Morgan Erlich | Eliana Abraham | All
| 2016-09-12 | Mon | NA | NA | NA
| 2016-09-14 | Wed | Done: Watched tutorial, set up project, delegated responsibilities Next: Collectable Item pickup Help: None yet | Done: Watched tutorial, set up project, delegated responsibilities Next: Grid based movement Help: Possible question about grid based system. Office hours??? | NA
| 2016-09-16 | Fri | Done: Collectable Item pickup Next: Damage Cooldown Help: None yet | Done: Finished setting up state machine, from tutorial Next: Grid based movement & Refining normal movement Help: Help with moonwalking problem and gird based movement | N/A
| 2016-09-19 | Mon | Done: Grid based movement and Stalfos Next: Camera Movement Help: None yet | Done: Grid Based Movement and started HUD Next: Finish Hud and weapon selection Help: making a new menu for weapon selection and telling when link used which weapons | Done: Grid Based Movement
| 2016-09-21 | Wed | Done: Camera Movement Next: Door Unlock Help: Enemy wall collisions | Done: Finished Hud (but not item selection) Next: Bomb functionality Help: making a new menu for weapon selection and telling when link used which weapons | N/A
| 2016-09-23 | Fri | Done: Door Unlock Next: Keese and GoriyaHelp: Debugging for alpha submission | Done: Got basic bomb functionality working Next: Refining bomb functionality and boomerang Help: making a new menu for weapon selection and telling when link used which weapons | Done: Collected notes for research and analysis Next: Compile research and analysis and write up level sketch Help: N/A
| 2016-09-26 | Mon | Done: Keese and Goriya basic movement Next: Wallmasters and Aquamentus Help: NA | Done: almost done with boomerang done sword and bomb done Next: with bow but still some bugs and continue to work on HUD Help: Boomerang | N/A
| 2016-09-28 | Wed | Done: Wallmasters and Aquamentus Next: Pushableblocks and enemy damage Help: NA | Done: almost done with boomerang with bow but still some bugs and continue to work on HUD Next: Item drops and tiles Help: Boomerang | N/A
| 2016-09-30 | Fri | Done: Pushableblocks and enemy damage Next: Speach engine room and cheat codes Help: NA | Done: Shield some hud item drops done. water tiles done Next: Boomerang, Hud, bomb, fix bugs Help: Boomerang Bom | Done: NA Next: Design custom level and mechanics Help: NA
| 2016-10-03 | Mon | Done: almost all of the custom level. Next: turnin Help: NA | Done: Hud, Most of Boomerang, hopefully maybe enemy, invincibility, bombs, keys for locked doors but that is a long shot Help: Everything :( | Done: Design custom level and mechanics Next: NA Help: NA
| 2016-10-03 | Mon
| 2016-10-03 | Mon
| 2016-10-03 | Mon
| 2016-10-03 | Mon
| 2016-10-03 | Mon